RESEARCH PROGRESS REPORT FOR THE QUARTER ENDING:

Wisconsin Department of Transportation

DT1241     2009

| ##### Research, Development and Technology Transfer |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Program: (Choose One) |  |  |  |  |  |  |  |  |  |
|  |  | ###### Policy Research |  |  |  |  | Pooled Fund TPF # 5(092) |  |  |
|  |  | Wisconsin Highway Research Program |  |  |  |  | Other |  |  |
| Project Title: |  |  | Developing and Evaluating Safe Winter Driving Messages |  |  |  |  |  |  |
| Administrative Contact/Phone #: |  |  |  | Colleen Bos/ (608) 577-4805 |  |  |  | WisDOT Project ID(s): | 0092-09-21 |
| WisDOT Technical Contact/Phone #: |  |  |  |  | Michael Sproul/ (608) 266-8680 |  |  | Other Project ID: |  |
| Project Investigator/Phone # (agency & contact): Craig Barnes, thembcgroup, 314.361.6717 |  |  |  |  |  |  |  | Approved Starting Date: | 5/28/2009 |
| WisDOT Comments: |  |  |  |  |  |  |  | Original End Date: | 12/31/2009 |
|  |  |  |  |  |  |  |  | Current End Date: | 12/31/2009 |
| Sponsor: Wisconsin Department of Transportation |  |  |  |  |  |  |  | Number of Extensions: | 0 |

| Schedule Status: |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | On schedule |  | Ahead of schedule |
|  |  | On revised schedule |  | Behind schedule (Please explain below) |

| #### Total Project Budget | Expenditures Current Quarter | Total Expenditures | % Funds Expended | % Work Completed |
| --- | --- | --- | --- | --- |
| $97,709.00 | $5,725.00 | $5,725.00 | .058 | 5% |

Project Description:

Progress This Quarter: (Includes project committee meetings, work plan status, contract status, significant progress, etc.)

Meetings:

- Kickoff teleconference with state PIOs on 5/28/09

- Phone conversations with Contract administrators and Wisconsin MBE and affirmative action compliance personnel.

- Teleconference with subcontractors on 6/10/09 to discuss data

Progress

- Analyzed first set of sample data from 4 states: Wisconsin, Nebraska, Vermont, Iowa

- Developed a query table indicating data needed for analysis

- Requested a 2 month sample of winter crash data from states

- Conducted internal meetings to further refine work plans and sub-contractor contributions

In Progress

- Currently receiving and reviewing 2 month sample data from states to determine which states have the most complete data sets

Anticipated Work Next Quarter:

- Depending response from participating states, mbc targets to have initial data findings ready for review for the Clear Roads Committee Meeting at the end of July

- Complete data analysis as suggested in task 1 to identify high risk groups, resultant crash characteristics, and individual driver behavior when roads are snow or ice covered

- Draft questions for surveys/focus group

- Conduct focus groups

- Initiate message development based on research findings

Circumstances Affecting Progress and/or Budget:

- NONE

Gantt Chart: