RESEARCH PROGRESS REPORT FOR THE QUARTER ENDING:

Wisconsin Department of Transportation

DT1241     2009

| ##### Research, Development and Technology Transfer |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Program: (Choose One) |  |  |  |  |  |  |  |  |  |
|  |  | ###### Policy Research |  |  |  |  | Pooled Fund TPF # 5(092) Clear Roads |  |  |
|  |  | Wisconsin Highway Research Program |  |  |  |  | Other |  |  |
| Project Title: |  |  | Development of a Toolkit for Cost-benefit Analysis of Specific Winter Maintenance Practices, Equipment and Operations |  |  |  |  |  |  |
| Administrative Contact/Phone #: |  |  |  | Colleen Bos/ (608) 577-4805 |  |  |  | WisDOT Project ID(s): | 0092-09-08 |
| WisDOT Technical Contact/Phone #: |  |  |  |  | Michael Sproul/ (608) 266-8680 |  |  | Other Project ID: | Clear Roads 08-02 |
| Project Investigator/Phone # (agency & contact): Xianming Shi, PhD, PE, Western Transportation Institute (WTI) Montana State University (406) 994-6486 |  |  |  |  |  |  |  | Approved Starting Date: | 12/17/2008 |
| WisDOT Comments: |  |  |  |  |  |  |  | Original End Date: | 8/31/2010 |
|  |  |  |  |  |  |  |  | Current End Date: | 8/31/2010 |
| Sponsor: Wisconsin Department of Transportation |  |  |  |  |  |  |  | Number of Extensions: | 0 |

| Schedule Status: |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | On schedule |  | Ahead of schedule |
|  |  | On revised schedule |  | Behind schedule (Please explain below) |

| #### Total Project Budget | Expenditures Current Quarter | Total Expenditures | % Funds Expended | % Work Completed |
| --- | --- | --- | --- | --- |
| $149,500.00 | $29,439.00 | $37,164.00 | 25% | 28% |

Project Description:

This project is the development of a toolkit that will provide winter maintenance managers a means by which to evaluate and justify expenditures on a variety of practices, equipment and operations. Specifically, this research aims to establish a practical toolkit that can be employed by maintenance managers not only to understand the expected costs and benefits of specific practices, equipment, or operations, and convey those expectations to decision-makers outside the maintenance community. The toolkit will include guidance related to the costs and benefits of practices, equipment, and operations, as well as provide a means to be expandable in the future to include additional winter maintenance elements as needed.

Progress This Quarter: (Includes project committee meetings, work plan status, contract status, significant progress, etc.)

Task 0. Project Management (35% completed)

This task involved periodic communications within the research team (e.g. weekly meetings) as well as between the research team and the sponsor. In June, 2009, a teleconference was held with the TAC to discuss the results of the initial survey and literature review.

Task 1. Comprehensive Literature Review (90% completed)

The literature review of the costs, benefits and effectiveness of winter maintenance practices, equipment and operations was completed during the quarter.  This was subsequently provided to the TAC for review and comment.  Based on the results of a conference call held with the TAC on June 25, 2009, some further additions will be made to this review prior to inclusion in the final project report.

Task 2. Survey of Best Practices (50% completed)

Work that was completed during this quarter on the development, administration and analysis of an initial survey of winter maintenance practitioners.  This survey focused on learning what practices, equipment and operations were presently used by agencies, as well as which ten of these items practitioners would like to see included in the toolkit to be developed.  Respondents also were asked what form they would like the toolkit to take, with a majority indicating that a web-based application was preferred. The results of the initial survey was submitted to and reviewed by the TAC.

Anticipated Work Next Quarter:

Work in the coming quarter will consist of two tracks.  First, a second round of surveys will be developed and administered to winter maintenance professionals to obtain specific information (costs, benefits, documentation) related to the top ten toolkit items identified during the first survey. These items included anti-icing, front and underbody blades, AVL/GPS, pavement temperature sensors, RWIS, deicing, MDSS, carbide blades, air temperature sensors, and zero velocity spreaders.

The second track of the work will focus on the initial development of the toolkit itself.  Based on the results of survey one, practitioners indicated that they would like the toolkit to take the form of a website applications.  Subsequently, initial work related to the development of this website will begin during the next quarter.  This will include the development of website mockups, as well as the identification of cost and benefit information that will incorporated as guidance in the tool itself.  Finally, initial coding work will also begin.

Circumstances Affecting Progress and/or Budget:

None at the present time.

Gantt Chart: