RESEARCH PROGRESS REPORT FOR THE QUARTER ENDING:

Wisconsin Department of Transportation

DT1241     2009

| ##### Research, Development and Technology Transfer |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Program: (Choose One) |  |  |  |  |  |  |  |  |  |
|  |  | ###### Policy Research |  |  |  |  | Pooled Fund TPF # 5(092) Clear Roads |  |  |
|  |  | Wisconsin Highway Research Program |  |  |  |  | Other |  |  |
| Project Title: |  |  | Development of Interface Specifications for Mobile Data Platforms on DOT Vehicles |  |  |  |  |  |  |
| Administrative Contact/Phone #: |  |  |  | Colleen Bos/ (608) 577-4805 |  |  |  | WisDOT Project ID(s): | 0092-09-09 |
| WisDOT Technical Contact/Phone #: |  |  |  |  | Michael Sproul/ (608) 266-8680 |  |  | Other Project ID: | Clear Roads 08-01 |
| Project Investigator/Phone # (agency & contact): Greg Thompson Thompson Engineering Company 651 260-0116 |  |  |  |  |  |  |  | Approved Starting Date: | 12/4/2008 |
| WisDOT Comments: |  |  |  |  |  |  |  | Original End Date: | 3/31/2010 |
|  |  |  |  |  |  |  |  | Current End Date: | 3/31/2010 |
| Sponsor: Wisconsin Department of Transportation |  |  |  |  |  |  |  | Number of Extensions: | 0 |

| Schedule Status: |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | On schedule |  | Ahead of schedule |
|  |  | On revised schedule |  | Behind schedule (Please explain below) |

| #### Total Project Budget | Expenditures Current Quarter | Total Expenditures | % Funds Expended | % Work Completed |
| --- | --- | --- | --- | --- |
| $49,500.00 | $9,690.00 | $19,030.00 | 38.4% | 38.4% |

Project Description:

The Clear Roads pooled fund research program (www.clearroads.org), in coordination with the Wisconsin Department of Transportation, seeks to develop communication and data format specifications to support mobile data platforms used by State DOT’s.  The mobile data platforms could be equipment such as, snow plows, end-loaders, supervisor trucks, paint trucks, herbicide sprayers, trailers, oil distributors and other similar equipment used in roadway maintenance operations.  Agencies that are considering adding GPS/AVL to support the mobile data platform need a set of specifications that will allow them to purchase a variety of different sensors that all use a common communication protocol and data format.

Progress This Quarter: (Includes project committee meetings, work plan status, contract status, significant progress, etc.)

1. Final Literature Search Report completed.

2. Created three surveys, posted them online, recorded results.

3. Draft Survey Results report submitted for review.

4. Quarterly Report plus four telephone conference calls.

Anticipated Work Next Quarter:

1. Final Survey Results Report completed.

2. Specifications development & preparation

3. Quarterly Report plus conference calls as needed

Circumstances Affecting Progress and/or Budget:

1. Excellent response for review of documents by Clear Roads members assists in on-schedule performance.

2. Judicious response from Clear Roads Project Manager & Champion on project issues contributes to on-schedule.

Gantt Chart:

See Figure 1 (Schedule) & Figure 2 (Task Flow) on next page.

Schedule

Figure 1: Schedule for Clear Roads Project

Task Flow Chart

Figure 2: Task Flow for Clear Roads Project