| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Snow Removal at Extreme Temperatures OBJECTIVES: To review best management practices for maintaining clear roads at extremely low temperatures and develop some cost effective strategies for getting the roadway to a bare/dry condition in extreme temperatures and keeping it at that condition. |  |  |
| PERIOD COVERED: July 1, 2012 – Dec. 31, 2012 |  |  |
| PARTICIPATING AGENCIES: Western Transportation Institute, Montana State University – Prime Dave Bergner and Sustainable Salting Solutions, LLC (Mark Cornwell) - Consultants |  |  |
| PROJECT MANAGER: Debra Fick LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Xianming Shi, Ph.D., P.E. | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $50,000 | PROJECT EXPENDITURES TO DATE: $29,647 |  |
| WORK COMPLETED: Project Management A teleconference was held on July 30 to discuss project progress and next steps. This task also involved periodic communications within the research team as well as between the research team and the sponsor. Task 1. Literature Review and Agency Surveys (100% completed) A draft literature review was sent to the project panel for review on June 18, 2012. A draft survey was sent to the project panel for review on May 15 and was distributed on June 5, 2012. As of June 30, 2012 there were 141 responses. Efforts were made to increase international responses. Task 2. Identifying Promising Strategies (100% Completed) In light of findings from the literature review and survey responses, the researchers narrowed down the promising strategies. Task 3. Cost-Benefit Analysis for Select Best Management Practices (0% completed) - This task was cancelled based on the panel’s suggestion since there was not enough significant BMPs identified and not enough data existed to support such cost-benefit analysis. Task 4. Recommending Best Management Practices (0% completed) - This task was cancelled since more research would be needed before one can recommend BMPs for winter maintenance at extreme temperatures. Task 5. Implementation Recommendations/Final Report/Presentation (95% completed) A draft final report will be submitted to the sponsor in Jan. 2013. |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: Work in the coming quarter will focus on addressing any comments the project panel may have on the draft final report and make it a more usable research product. |  |  |
| STATUS AND COMPLETION DATE: On budget and on schedule. Start and completion dates of this project: March 20, 2012 - Jan. 31, 2013. |  |  |