| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Cost-Benefit Analysis Toolkit – Phase II OBJECTIVES: To expand upon and improve the winter maintenance cost/benefit analysis toolkit Phase I. |  |  |
| PERIOD COVERED: Oct. 1, 2012 – Dec. 31, 2012 |  |  |
| PARTICIPATING AGENCIES: Western Transportation Institute, Montana State University – Prime Current Transportation Solutions Inc. - Consultants |  |  |
| PROJECT MANAGER: Debra Fick LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Xianming Shi, Ph.D., P.E. | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $109,999 | PROJECT EXPENDITURES TO DATE: $55,897 (plus approximately $30,000 on the subcontract for the completed tasks in the last quarter, which was not invoiced until Jan. 2013). |  |
| WORK COMPLETED: Project Management A few project meetings were held during the last quarter to allow the project PI and co-PI to report the project progress to the project TAC and to discuss next steps. A no-cost 3-month time extension was requested by the team and approved by the sponsor in Jan. 2013. Task 1. Phase I Enhancements (100% completed) The enhancements mainly include: ensuring the tool runs on more versions of Internet browsers and generating reports in a format that can be more easily manipulated for presentation to managers. The enhanced toolkit also includes the capability of allowing a user to save multiple scenarios and revisit them. We also include some photos for items in this toolkit to enhance its usability. A Task 1 memo was submitted in early July 2012. Task 2. Survey to Identify Another Ten Items (100% completed) The research team prioritized the new top ten items for this toolkit via a survey of practitioners. Task 3. Data Elements for Cost-Benefit Analysis (100% completed) The research team gathered most of the data for the new top ten items needed for cost-benefit analysis. Then, the research team contacted appropriate contacts in the Clear Roads group to complete this task. Task 4. Methodologies and Assumptions for Cost-Benefit Analysis (100% completed) The research team established the methodologies and assumptions for the cost-benefit analysis of the new top ten items. Task 5. Website Implementation and User’s Guide (70% completed) Through an iterative process, the research team worked with the programmer to implement the new website (with the new top ten items). The User’s Guide has been updated in Jan. 2013 (even though not in the last quarter). Task 6. Final Report/Presentation/Training Session (0% completed) |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: Work in the coming quarter will consist of three tracks, i.e., continue and complete the Tasks 4-6. |  |  |
| STATUS AND COMPLETION DATE: On time and on schedule. Start and (new) completion dates of this project: Feb. 6, 2012 – April 30, 2013. |  |  |