| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Cost-Benefit Analysis Toolkit – Phase II OBJECTIVES: To expand upon and improve the winter maintenance cost/benefit analysis toolkit Phase I. |  |  |
| PERIOD COVERED: July 1, 2012 – Oct. 31, 2012 |  |  |
| PARTICIPATING AGENCIES: Western Transportation Institute, Montana State University – Prime Current Transportation Solutions Inc. - Consultants |  |  |
| PROJECT MANAGER: Debra Fick LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Xianming Shi, Ph.D., P.E. | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $109,999 | PROJECT EXPENDITURES TO DATE: $44,311 |  |
| WORK COMPLETED: Project Management A project meeting (via teleconference) was held on July 31, 2012 to allow the co-PI to report the project progress to the project TAC and to discuss next steps. Task 1. Phase I Enhancements (100% completed) The enhancements mainly include: ensuring the tool runs on more versions of Internet browsers and generating reports in a format that can be more easily manipulated for presentation to managers. The enhanced toolkit also includes the capability of allowing a user to save multiple scenarios and revisit them. We also include some photos for items in this toolkit to enhance its usability. A Task 1 memo was submitted in early July. Task 2. Survey to Identify Another Ten Items (100% completed) The research team has prioritized the new top ten items for this toolkit via a survey of practitioners. Task 3. Data Elements for Cost-Benefit Analysis (80% completed) The research team has gathered most of the data for the new top ten items needed for cost-benefit analysis. We will continue to contact appropriate contacts in the Clear Roads group to complete this task. Task 4. Methodologies and Assumptions for Cost-Benefit Analysis (80% completed) The research team has established the majority of methodologies and assumptions for the cost-benefit analysis of the new top ten items. Task 5. Website Implementation and User’s Guide (30% completed) Task 6. Final Report/Presentation/Training Session (0% completed) |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: Work in the coming quarter will consist of three tracks, i.e., continue and complete the Tasks 3-5. |  |  |
| STATUS AND COMPLETION DATE: On time and on schedule. Start and completion dates of this project: Feb. 6, 2012 - Jan. 31, 2013. |  |  |