| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Understanding the True Cost of Snow and Ice Control OBJECTIVES: Create a tool to communicate the maintenance level of service that can be bought by different budget levels. Compare at a high level the true cost of winter maintenance experienced at an aggregate level by states. |  |  |
| PERIOD COVERED: April 1, 2012 to June 30, 2012 |  |  |
| PARTICIPATING AGENCIES: Minnesota Department of Transportation and the Clear Roads Technical Advisory Committee |  |  |
| PROJECT MANAGER: Debra Fick LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: David Rose, Parsons Brinckerhoff Andrew Cadmus, Parsons Brinckerhoff | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $192,720 | PROJECT EXPENDITURES TO DATE: $23,462 |  |
| WORK COMPLETED: - Collected, analyzed and consolidated data - Assessed ability of data to support objectives - Revisited objectives to meet data availability - Developed new methodology for moving forward |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: - Complete data collection and assessment - Begin development of prototype tool to meet objectives |  |  |
| STATUS AND COMPLETION DATE: This research projects is well underway in the data collection and assessment phase. New methodology has been developed to meet the objectives given limited data available. Completion is expected December 2012. |  |  |