| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Understanding the True Cost of Snow and Ice Control OBJECTIVES: Create a tool to communicate the maintenance level of service that can be bought by different budget levels. Compare at a high level the true cost of winter maintenance experienced at an aggregate level by states. |  |  |
| PERIOD COVERED: April 1, 2013 to June 30, 2013 |  |  |
| PARTICIPATING AGENCIES: Minnesota Department of Transportation and the Clear Roads Technical Advisory Committee |  |  |
| PROJECT MANAGER: Debra Fick LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: David Rose, Parsons Brinckerhoff Andrew Cadmus, Parsons Brinckerhoff | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $192,720 | PROJECT EXPENDITURES TO DATE: $103,221 (30Jun13) |  |
| WORK COMPLETED: - Reviewed next steps with Clear Roads team - Integrated feedback from team into prototype tool - Identified any next steps desired to be completed prior to contract close-out - Completed draft of final report - Submitted final prototype tool |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: - Expand final report to include additional information regarding data collection - Expand final report to include detailed analysis of Maine’s expenditure data - Develop checklist and sample database to support data collection - Host final webinar for Clear Roads TAC - Submit final report and final prototype tool |  |  |
| STATUS AND COMPLETION DATE: A new methodology has been developed due to the limited data available. A prototype tool has been developed and has been accepted by the Clear Roads team. A draft report was submitted, but the Clear Roads team requested additional information regarding data collection and a more thorough explanation of the analysis completed with Maine’s data. These changes require an extension of contract time to October 31, 2013. This is a no-cost extension because the task is still well within budget. The request for a no-cost time extension has been submitted. |  |  |