# Memorandum

To:	Clear Roads Technical Advisory Committee

From:	Keith Pilgrim

Subject:	Quarterly Project Update

Date:	2/4/2013

Project:	Determining the Toxicity of Deicing Materials: MnDOT Contract #99083

The primary project activity during this quarter was the completion of a series of whole effluent toxicity tests with eight deicing chemicals and several doses per chemical.  This test series, which included testing with Ceriodaphnia dubia, fathead minnow, and Selenastrum capricornutum, was designated as the “full test,” and was conducted determine the toxicity of the deicing chemicals.  Toxicity endpoints were calculated.  Results were presented to the committee.