| State Planning and Research Program Quarterly Report |
| --- |
| PROJECT TITLE: Cost-Benefit of Various Winter Maintenance Strategies OBJECTIVES: • Assess and communicate the costs and benefits of at least three winter maintenance strategies to understand the safest and most cost-effective approach based on the desired level of service (LOS) |
| PERIOD COVERED: Jan. 1, 2014 – Mar. 31, 2014 |
| PARTICIPATING AGENCIES: Western Transportation Institute, Montana State University – Prime SRF Consulting Group, Inc.- Subcontractor |
| PROJECT MANAGER: Tom Peters LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: David Veneziano, Ph.D. | SP&R PROJECT NO: | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $121,730 | PROJECT EXPENDITURES TO DATE: $22,632 |
| WORK COMPLETED: Project Management Project management activities during the quarter were focused on budget and timeline maintenance. To date, the project is on budget and time. Task 1. Review Existing Research (70% completed) The researchers continued the literature search which focuses on the costs and benefits that result from various winter maintenance strategies. This review is focused on information which is relevant to the components of the three maintenance strategies outlined by the project panel and discussed during the kickoff teleconference. Work to date has identified relevant documents and summarized this information in the Task 1 deliverable document. This document will be completed and delivered to the project panel in April. Task 2. Survey (5% completed) Based on the results of Task 1 and any informational gaps from existing research that were identified, the researchers will conduct a survey of Clear Roads member states, as well as U.S. and international winter maintenance professionals to address those gaps. To date, existing data/information and data gaps are being identified which will be presented to survey participants for verification and feedback. Task 3. Analysis and Organization (0% completed) The researchers will analyze the information gathered in Tasks 1 and 2 to characterize and organize the cost and benefit information presented by each document. This information will further be organized into a matrix that presents the specific costs and benefits (and any other pertinent information) of each of the strategies Task 4. Final Report (0% completed) The researchers will prepare and submit a final report of the work completed, including an executive summary, introduction, methodology, results for each task, the cost and benefit matrix, and conclusions. |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: Work in the coming quarter will consist of Task 1: Complete the review of existing research on the costs and benefits of the panel-specified winter maintenance strategies that are the focus of the project and deliver a task report on that information to the project panel for review and comment. The Task 2 survey will also be developed and conducted during the upcoming quarter. |
| STATUS AND COMPLETION DATE: On time and on schedule. Completion date – January 31, 2015 |