| State Planning and Research Program Quarterly Report |
| --- |
| PROJECT TITLE: Training for Supervisors and Operators OBJECTIVES: The goal of this project is to develop a comprehensive, easy-to-use training program for winter maintenance supervisors and operators. Under this contract, our team will work with the Minnesota Department of Transportation and Clear Roads Technical Advisory Committee to identify and compile the many resources on winter maintenance and develop a series of 18 training modules for supervisors, seasoned operators, and new operators for use in the classroom or online. Information gathered through synthesis is only valuable if it can be effectively transmitted in clearly prepared documents and materials. |
| PERIOD COVERED: September 1, 2015 – December 31, 2014 |
| PARTICIPATING AGENCIES: Clear Roads DOTs: Kansas, Rhode Island, Iowa, Maine, Oregon, Missouri, Ohio, South Dakota, Washington, Illinois, Minnesota, Nebraska, Connecticut, Pennsylvania, Massachusetts, Michigan, California, Wyoming, Vermont, Wisconsin, North Dakota, Vermont, Virginia, Montana, Idaho, Utah, Colorado, New York Federal Highway Administration |
| PROJECT MANAGER: Colleen Bos, CTS LEAD AGENCY: Minnesota Department of Transportation PRINCIPAL INVESTIGATOR: Jim Grothaus, University of Minnesota | SP&R PROJECT NO: MnDOT Contract No. 99008 Work Order No. 168 | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $100,000 | PROJECT EXPENDITURES TO DATE: It is an 18 month contract. We have completed 1/6 (3months) of the work. An estimate of the amount of spent to date would be: $16,667.00 |
| WORK COMPLETED: To date the project team has developed the following modules Plowing procedures Truck operations These two modules (Task 2) are waiting for a technical review from Clear Roads Additionally we have worked on the following modules: Science of Freeze Point Depressants Prewetting Spreading Principles of Ice Formation Material Use |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: We anticipate approval of the 2 completed modules. Meet and review the materials with the Technical Advisory Panel (TAP). Work on modules 3-6 and review them with the TAP. Work with the TAP to determine how the training modules will be displayed on the internet and develop a plan to start sharing the completed training modules the participating clear roads members. |
| STATUS AND COMPLETION DATE: We have approval of Task 1 of the contract and are waiting for approval of Task 2. |