| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Environmental Factors Causing Fatigue in Equipment Operators during Winter Operations OBJECTIVES: The goal is to develop a series of cost effective, realistic recommendations for reducing or eliminating fatigue that impacts equipment operators during winter operations. |  |  |
| PERIOD COVERED: July 2012 to September 2012 |  |  |
| PARTICIPATING AGENCIES: Minnesota Department of Transportation and the Clear Roads Technical Advisory Committee |  |  |
| PROJECT MANAGER: Debra Fick/ Tom Peters LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Jeff Hickman | SP&R PROJECT NO: MnDot Contract# 99084 | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $124,991 (total) | PROJECT EXPENDITURES TO DATE: (as of 9/30/2012) $181.18 |  |
| WORK COMPLETED: - Kickoff meeting was held on August 2, 2012 with project personnel and the Clear Roads Technical Advisory Committee. The purpose of the kickoff meeting was to review project tasks and goals. - Task 1 Literature Search. In Task 1, the VTTI team conducted a literature review to identify factors that cause driver fatigue during winter maintenance operations. This review considered all types of factors including elements of trucks, sleep deprivation, winter conditions, cold temperatures, traffic, scheduling/shift policies, and equipment. The draft literature search was sent to the Steering Committee on September 28, 2012 for review. - A conference call on the task 1 activities was held on September 28, 2012. VTTI personnel and the Clear Roads Technical Advisory Committee participated in the conference call. - VTTI personnel meet with Allen Williams and David Clarke from the Virginia Department of Transportation (VDOT) on September 13, 2012 to discuss next steps regarding the implementation of task 3. |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: - The Task 1 Literature Search will be completed - VTTI will begin work on the Task 2 survey. During the next reporting period, VTTI will develop the draft survey instruments, identify survey respondents, and receive Virginia Tech Institutional Review Board (IRB) approval to conduct the survey. - VTTI will begin work on task 3. It’s likely that a pilot test of the data collection systems on VDOT trucks will be completed during the next reporting period. A preliminary date of October 26, 2012 has been scheduled for driver recruitment. |  |  |
| STATUS AND COMPLETION DATE: No problems to report. On schedule to complete project in October 2013. |  |  |