| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Environmental Factors Causing Fatigue in Equipment Operators during Winter Operations OBJECTIVES: The goal is to develop a series of cost-effective, realistic recommendations for reducing or eliminating fatigue that impacts equipment operators during winter operations. |  |  |
| PERIOD COVERED: April 2013 to June 2013 |  |  |
| PARTICIPATING AGENCIES: Minnesota Department of Transportation and the Clear Roads Technical Advisory Committee |  |  |
| PROJECT MANAGER: Debra Fick/Tom Peters LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Jeff Hickman | SP&R PROJECT NO: MnDot Contract# 99084 | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $124,991 (total) | PROJECT EXPENDITURES TO DATE: (as of 6/30/2013) $37,185.53 |  |
| WORK COMPLETED: - The Virginia Tech Transportation Institute (VTTI) finalized the Task 2 survey. - VTTI completed naturalistic data collection from two instrumented Virginia Department of Transportation (VDOT) trucks. - Data collection activities for the operator and safety manager questionnaires have been completed. Approximately 900 operators and 300 safety managers completed the surveys. |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: - VTTI will complete data reduction activities for the naturalistic driving data. - VTTI will complete data analyses of the operator and safety manager questionnaires. |  |  |
| STATUS AND COMPLETION DATE: No problems to report. On schedule to complete project in October 2013. |  |  |