| State Planning and Research Program Quarterly Report |  |  |
| --- | --- | --- |
| PROJECT TITLE: Environmental Factors Causing Fatigue in Equipment Operators during Winter Operations OBJECTIVES: The goal is to develop a series of cost-effective, realistic recommendations for reducing or eliminating fatigue that impacts equipment operators during winter operations. |  |  |
| PERIOD COVERED: October to December 2012 |  |  |
| PARTICIPATING AGENCIES: Minnesota Department of Transportation and the Clear Roads Technical Advisory Committee |  |  |
| PROJECT MANAGER: Debra Fick / Tom Peters LEAD AGENCY: Mn/DOT PRINCIPAL INVESTIGATOR: Jeff Hickman | SP&R PROJECT NO: MnDot Contract# 99084 | PROJECT IS: Planning X Research & Development |
| ANNUAL BUDGET: $124,991 (total) | PROJECT EXPENDITURES TO DATE: (as of 12/20/2012) $4,994.07 |  |
| WORK COMPLETED: - The Task 1 Literature Search was completed and sent on November 30, 2012. - The Virginia Tech Transportation Institute (VTTI) began work on the Task 2 survey. VTTI developed the draft survey instruments. - Virginia Tech Institutional Review Board (IRB) approval for the naturalistic data collection effort (Task 3) was received on December 4, 2012. - VTTI began work on Task 3. Recruitment activities were completed on November 26, 2012. A total of four drivers agreed to participate in the study. |  |  |
| SUMMARY OF ACTIVITIES EXPECTED TO BE PERFORMED NEXT QUARTER: - The Task 1 Literature Search will be revised based on feedback received on December 19, 2012. - VTTI will complete the Task 2 survey and receive Virginia Tech IRB approval to conduct the survey. - VTTI will instrument two Virginia Department of Transportation (VDOT) trucks, conduct a pilot test of the data collection systems on VDOT trucks, and begin data collection during the next reporting period. |  |  |
| STATUS AND COMPLETION DATE: No problems to report. On schedule to complete project in October 2013. |  |  |